## Project_Info
Project Name | Project Owner | Version | Created On | Description
Smart Traffic Violation Pattern Detector | Ishwari Deshmukh | 1.0 | 2025-12-08 | Interactive Streamlit dashboard to analyze traffic violation patterns, hotspots, fines, and weather effects.

## Product_Backlog
ID | Title | Description | Priority | Estimate (days)
PBI-001 | Data Ingestion & Cleaning | Implement robust CSV loader, dtype fixes, date/time parsing | High | 2
PBI-002 | Home Page & About Page | Create Home and About pages with hero image and project description | Medium | 1
PBI-003 | Overview Dashboard | Top violations, top locations, metrics | High | 2
PBI-004 | Violation Types View | Countplot for violation types with top-N | Medium | 1
PBI-005 | Hotspots View | Top hotspot locations and bar chart | Medium | 1
PBI-006 | Payment & Fines Analysis | Distribution, histplot and fines by vehicle type | High | 2
PBI-007 | Weather & Conditions View | Weather condition countplot | Low | 1
PBI-008 | Average Fine per Location | Compute and visualise avg fine per location | Medium | 2
PBI-009 | Assets & Images | Add assets images (T01.jpg, T03.jpg, T04.jpg) | Low | 1
PBI-010 | Export & Reporting | Allow CSV/Excel export of summary tables | Low | 1

## Sprint_Plan
Sprint | Duration | Goals | Items
Sprint 1 | 2 weeks | Data ingestion, Home/About, Overview | PBI-001,PBI-002,PBI-003
Sprint 2 | 2 weeks | Violations, Hotspots, Payment & Fines | PBI-004,PBI-005,PBI-006
Sprint 3 | 2 weeks | Weather, Avg Fine, Assets, Export | PBI-007,PBI-008,PBI-009,PBI-010