## Defects
Defect ID | Reported On | Reporter | Summary | Severity | Priority | Status | Assigned To | Steps to Reproduce | Expected Result | Actual Result
D-001 | 2025-12-08 | QA | App crashes when default dataset path missing | High | High | Open |  | Start app without uploaded file and without default path | Show friendly error and allow upload | st.error and empty dataframe, some code paths assume df exists
D-002 | 2025-12-08 | QA | st.image called with width='stretch' causes rendering issue | Medium | Medium | Open |  | Load Home page when assets/T03.jpg missing | Graceful fallback text | Streamlit may raise type error for width parameter
D-003 | 2025-12-08 | QA | Pie chart too small on some screens (figsize 2.5) | Low | Low | Open |  | Open Vehicle_Type VS Fine_Amount | Readable pie chart | Tiny pie chart